## WBS
Task | Notes | Detail | Summary | Resource | Assigned to | Status | Plan
Develop migration strategy SourceSafe | Includes .net |  | 6 |  | Paul H. | In-Progress | 8/22 - 8/26
Review migration options |  | 4 |  | TA
Determine migration method |  | 2 |  | TA |  |  |  | 2nd update
Test migration method
Develop migration strategy SVN |  |  | 6 |  | Jason T. | Done
Review migration options |  | 4 |  | TA
Determine migration method |  | 2 |  | TA
Test migration method
Migrate SVN repository data | Includes Webcenter |  | 12 |  | Jason T. |  | 9/5 - 9/9
Develop migration strategy |  | 2 |  | TA
Transfer production data |  | 4 |  | TA
Setup and configure migration toolset |  | 2 |  | TA
Resolve technical issues |  | 4 |  | TA
Migrate SourceSafe repository data |  |  | 12 |  | Paul H. |  | 8/29 - 9/2
Develop migration strategy |  | 2 |  | TA
Transfer production data |  | 4 |  | TA
Setup and configure migration toolset |  | 2 |  | TA
Resolve technical issues |  | 4 |  | TA
Train users |  |  | 8 |  | Jason T. |  | 9/12 - 9/16
Create training plan |  | 2 |  | Me
Develop training requirements |  | 2 |  | TA
Deliver training |  | 4 |  | TA
Integrate developer IDE's |  |  | 6 |  | Paul H.
Determine tool plugins |  | 2 |  | TA
Download and setup toolset plugins |  | 4 |  | TA
Test toolset integration |  |  | 10 |  | Paul H.
Create POC use cases |  | 2 |  | TA
Execute use cases |  | 4 |  | TA
Resolve technical issues |  | 4 |  | TA
Change Management |  |  | 4 |  | Jason T. |  | 9/19 - 9/23
Update development process documents/wiki's/websites | Discussed Github homepage | 2 |  | TA
Create email communication |  | 2 |  | TA
Total |  |  | 64

## Sheet1
GitHub Desktop as Standard
GitHub Flow may be the standard | May require more discussion