## WBS
Task | Detail | Summary | Resource | Assigned to
Develop migration strategy SourceSafe |  | 6 |  | Paul H.
Review migration options | 4 |  | TA
Determine migration method | 2 |  | TA
Test migration method
Develop migration strategy SVN |  | 6 |  | Jason T.
Review migration options | 4 |  | TA
Determine migration method | 2 |  | TA
Test migration method
Migrate SVN repository data |  | 12 |  | Jason T.
Develop migration strategy | 2 |  | TA
Transfer production data | 4 |  | TA
Setup and configure migration toolset | 2 |  | TA
Resolve technical issues | 4 |  | TA
Migrate SourceSafe repository data |  | 12 |  | Paul H.
Develop migration strategy | 2 |  | TA
Transfer production data | 4 |  | TA
Setup and configure migration toolset | 2 |  | TA
Resolve technical issues | 4 |  | TA
Train users |  | 8 |  | Jason T.
Create training plan | 2 |  | Me
Develop training requirements | 2 |  | TA
Deliver training | 4 |  | TA
Integrate developer IDE's |  | 6 |  | Paul H.
Determine tool plugins | 2 |  | TA
Download and setup toolset plugins | 4 |  | TA
Test toolset integration |  | 10 |  | Paul H.
Create POC use cases | 2 |  | TA
Execute use cases | 4 |  | TA
Resolve technical issues | 4 |  | TA
Change Management |  | 4 |  | Jason T.
Update development process documents/wiki's/websites | 2 |  | TA
Create email communication | 2 |  | TA
Total |  | 64